## Dashboard
PROJECT REPORTING DASHBOARD
DATE | TOTAL ITERATION | 2 | SPRINT 1 START DATE | ITERATION DURATION | 1.5 days | SPRINT 2 START DATE | Team Size
Note:- To view the Burndown chart for a particular day the next day should be selected in the Sprint Progress dropdown. For viewing the complete Sprint Burndown chart the status should be set to completed in the dropdown

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | US-01 | As a visitor, I should be able to login to the application by providing my credentials i.e. – contact number and password, so that I can avail all the services of the application. | MUST HAVE | 2 | 1084726 | 3- Completed
1 | 1 | US-02 | As a visitor, I should be able to “Register” with the application, by providing details like name, email id, contact number and password, so that, I can use the services and get the benefits of a registered user. | MUST HAVE | 3 | 1084726 | 3- Completed
1 | 1 | US-03 | As a visitor or a registered user, I should be able to see Hot deals that are available and search for other available packages, so that I can explore all the packages available for booking | SHOULD HAVE | 5 | 1084726 | 3- Completed
1 | 1 | US-04 | As a visitor or a registered user, I should be able to view package details, so that I can review the whole package. | SHOULD HAVE | 5 | 1084726 | 3- Completed
2 | 2 | US-05 | As a logged-in user, I should be able to Book a desired package. | MUST HAVE | 8 | 1084726 | 3- Completed
2 | 2 | US-06 | As a logged-in user, I should be able to view my planned trips. | SHOULD HAVE | 5 | 1084726 | 3- Completed
2 | 2 | US-07 | As a logged-in user, I should be able cancel a particular booking. | SHOULD HAVE | 3 | 1084726 | 3- Completed
2 | 2 | US-08 | As a logged-in user, I should be able to logout. | SHOULD HAVE | 2 | 1084726 | 3- Completed
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on F2: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 25 | 19.5 | 6 | 0
SPRINT 1 BACKLOG
US-01 | T1 | Validated all input fields in login component | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1
| T2 | Proper error messages are provided in the form | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
| T3 | Resolved the errors in the console | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 2 | 2
| T4 | Applied user functionalities for the logged user | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 3 | 3
| T1 | Inserted registeres user data into database of backend | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1
| T2 | Validated all input fields in register component | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 2 | 2
US-02 | T3 | Prepared new component for registration of users in the front end | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
| T4 | Resolved errors in console in backend | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1
| T5 | Applied react for login and registration forms | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 2 | 1 | 1
| T1 | Displayed all the hot deals available | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1
| T2 | Displaying package destination details the user has searched for | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 2 | 1 | 1
| T3 | Viewing details of package is done | 8/5/2020 | 8/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
US-03 | T4 | Styling done using bootstrap classes | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1
| T5 | Resolving errors from hotdeal-frontend | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5 | 0.5
| T1 | Display details of selected package in side bar | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 1 |  | 1
| T2 | Overview,itinery,book tabs coded | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 2 | 1 | 1
| T3 | Resolved errors in console | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 1 |  | 1
US-04 | T4 | styling done using bootstrap classes and displayed view packages | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 1 | 0.5 | 0.5
| T1 | log-out coding-frontend | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1
| T2 | Dialog-box was displayed | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
US-08 | T3 | functionalities for logout are coded | 11/5/2020 | 11/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 2 work

## Sprint II Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 12.5 | 7.5 | 6 | 0
SPRINT 2 BACKLOG
US-05 | T1 | checking if user has logged in before and displaying proper message if not logged in | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
| T2 | validating input fields of book component and displaying proper error messages | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
| T3 | booking confirmation and adding user data to database | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1
| T4 | Resolving errors in console | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
| T5 | Tested for proper functionality | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
US-06 | T1 | checking if user his logged in | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
| T2 | Displaying packages booked by logged in user | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 1 | 0.5 | 0.5
| T3 | Displaying error messages in case of error | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
| T4 | Resolving errors in console | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1 | 0.5
| T5 | Checking functionality | 12/5/2020 | 12/5/2020 | 1084726 | Coding | 3- Completed | 0.5 | 0.5
US-07 | T1 | Acess to planned trips | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 0.5 |  | 0.5
| T2 | Prompting user to confirm cancellation | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 0.5 |  | 0.5
| T3 | data deletion in backend once cancellation is confirmed | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 1 | 1 | 0.5
| T4 | Resolving errors in console | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 0.5 |  | 0.5
| T5 | Testing functionality | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 0.5 |  | 0.5
US-02 | T1 | Resolving errors in register | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 1 |  | 1
| T2 | testing functionality | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 0.5 |  | 0.5
US-03 | T1 | Resolving errors in backend | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 1 | 0.5 | 0.5
| T2 | checking functionality | 13/5/2020 | 13/5/2020 | 1084726 | Coding | 3- Completed | 0.5 |  | 0.5
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 2 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
| 1 | 8/5/2020 | 11/5/2020 | Sai Teja Nadakuditi | started using bootstrap classes | using unappropriate variable names | focus on coding | referred bootstrap courses from lex
| 2 | 8/5/2020 | 11/5/2020 | Sai Teja Nadakuditi | improving forms responsiveness | writing unwanted console statements | trying different react classnames | referring react material from lex
| 3 | 8/5/2020 | 11/5/2020 | Sai Teja Nadakuditi | using material ui | using unwanted functions | Asking doubts | Referring material ui site
| 4 | 12/5/2020 | 13/5/2020 | Sai Teja Nadakuditi | using gulp,linting | always using html and css | using linting | Referring stackoverflow

## Reference Data
SPRINT I BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual | TEAM VELOCITY CHART
1 | 1 | 25 | 25.5
| 2 | 16.67 | 19.5 | Sprint | Planned | Actual
| 3 | 8.34 | 6 | 1 | 25 | 25.5
|  |  |  | 2 | 12.5 | 13.5
SPRINT II BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual
2 | 1 | 12.5 | 13.5
| 2 | 8.33 | 7.5
| 3 | 4.16 | 6
Note on E6: Effort hours pending after day 1 of sprint 1
Note on E7: Effort hours pending after day 2 of sprint 1
Note on H7: Planned hours of effort in Sprint 1
Note on I7: Story points completed in sprint 1
Note on H8: Planned hours of effort in Sprint 2
Note on I8: Story points completed in Sprint 2
Note on E15: Effort hours pending after day 1 of sprint 2
Note on E16: Effort hours pending after day 2 of sprint 2

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
1 | US-02 | 1 | 1084726 | Register component with validations and errors | some of the validations for contact number failed | trial and error to get proper validations
1 | US-03 | 1 | 1084726 | obtaining hotdeals by creating package component | All packages are displayed instead of hotdeals | proper functionalities were written
1 | US-04 | 2 | 1084726 | implementing package at backend | package images were viewed only after clicking view details button | proper functionalities were written
2 | US-05 | 3 | 1084726 | booking component implementation | retrieving data of confirmed bookings | added sessions storage
2 | US-07 | 4 | 1084726 | cancellation of booking to be done | data wasn't getting deleted in database | debugging functionalities
1 | US-08 | 2 | 1084726 | implementation of dialog box | refreshing after logout | removed unwanted set timeout

## Product Backlog Grooming
Sprint | US ID | Points Discussed